## Detailed Project Plan
Project Plan - ID - EATGOOD TECHNOLOGIES PRIVATE LIMITED |  | Planned Start Date |  | Planned Go-Live Date
Go Live Date (Ready for Deployment) ID |  | 2025-03-03 |  | 2025-05-09
WBS No. | Project Phase/Activity | Responsibility | Tentative no. of days | Planned Start Date | Planned End Date | Status | Remarks
EI-01 | Prekickoff & Pre-requisites |  | 7 | 2025-03-03 | 2025-03-12 | Completed
EI-01.01 | Team Introduction and Project Overview | Shubham | 0.25 | 2025-03-03 | 2025-03-03 | Completed
EI-01.02 | Share prerequisites document and share Project Plan | Shubham | 0.25 | 2025-03-03 | 2025-03-03 | Completed
EI-01.03 | Provide Zoho Dev and QA server access (Including Middleware if any) | EATGOOD Team | 0.25 | 2025-03-03 | 2025-03-03 | Completed
EI-01.04 | Create UAT account (prod demo account) for ID | Clear - Shubham | 0.25 | 2025-03-03 | 2025-03-03 | Completed
EI-01.05 | Share Auth Token, PAN and GSTIN activation in Portal | Clear - Shubham | 0.25 | 2025-03-03 | 2025-03-04 | Completed
EI-01.06 | Creation of ERP Instance ID | EATGOOD Team | 3 | 2025-03-04 | 2025-03-07 | Completed
EI-01.07 | Maintain connection parameters in Zoho (Quality to Clear Sandbox) | Clear - Rohan | 0.25 | 2025-03-07 | 2025-03-07 | Completed
EI-01.08 | Test Connectivity from ERP | Clear - Rohan | 1 | 2025-03-07 | 2025-03-10 | Completed
EI-01.09 | Developer and functional to confirm access and connectivity | Clear - Rohan | 0.25 | 2025-03-10 | 2025-03-10 | Completed
EI-01.10 | Developer to share config. File to be updated in sandbox system | Clear - Rohan | 0.25 | 2025-03-10 | 2025-03-11 | Completed
EI-01.11 | Details (Period of extraction , system of extraction ) to be provided to developer | EATGOOD Team | 1 | 2025-03-11 | 2025-03-12 | Completed
EI-02 | Requirement Gathering Sign off |  | 7 | 2025-03-12 | 2025-03-21 | Completed
EI-02.01 | Plan Kick Off Call | Clear - Shubham | 1 | 2025-03-12 | 2025-03-13 | Completed
EI-02.02 | Solution Clarification to Client | Clear - Rohan | 2 | 2025-03-13 | 2025-03-17 | Completed
EI-02.04 | Review solution clarification & Q&A meetings | Clear - Rohan +Eatgood | 2 | 2025-03-17 | 2025-03-19 | Completed
EI-02.05 | Solution Clarification Sign off | EATGOOD Team | 2 | 2025-03-19 | 2025-03-21 | Completed
EI-03 | Implementation and Data Validation |  | 26 | 2025-03-21 | 2025-04-28 | In Process
EI-03-01 | Configuring to allow API calls in ZOHO Sandbox | Clear - Rohan | 1 | 2025-03-21 | 2025-03-24 | Completed
EI-03-02 | Calling Zoho APIs to fetch Invoice Details | Clear - Rohan | 1 | 2025-03-24 | 2025-03-25 | Completed
EI-03-03 | Sending the Invoice details to Clear Portal | Clear - Rohan | 1 | 2025-03-25 | 2025-03-26 | Completed
EI-03-04 | Calling Zoho APIs to fetch Vendor Details | Clear - Rohan | 1 | 2025-03-26 | 2025-03-27 | In Process
EI-03-05 | Sending the Vendor details to Clear Portal | Clear - Rohan | 1 | 2025-03-27 | 2025-03-28 | In Process
EI-03-06 | Calling Zoho APIs to fetch CN/DN Details | Clear - Rohan | 1 | 2025-03-28 | 2025-03-31 | In Process
EI-03-07 | Sending the CN/DN details to Clear Portal | Clear - Rohan | 1 | 2025-03-31 | 2025-04-01 | In Process
EI-03-08 | Calling Zoho APIs to fetch Payment Details | Clear - Rohan | 1 | 2025-04-01 | 2025-04-02 | In Process
EI-03-09 | Sending the Payment details to Clear Portal | Clear - Rohan | 1 | 2025-04-02 | 2025-04-03 | In Process
EI-03-10 | Update Invoice details (Discount, Payment Terms, Due Date, Invoice accepted Date) in ZOHO if Eatgood team accepts the Discount | Clear - Rohan | 3 | 2025-04-03 | 2025-04-08 | In Process
EI-03-11 | Calling the postingAck API when the Invoice details are updated in ZOHO | Clear - Rohan | 2 | 2025-04-08 | 2025-04-10 | In Process
EI-03-12 | Observation Discussion with End Users | Clear - Rohan | 3 | 2025-04-10 | 2025-04-15 | Not Started
EI-03-13 | End to End Functional testing - Deployment of Codes to Sandbox | Clear - Rohan | 1 | 2025-04-15 | 2025-04-16 | Not Started
EI-03-14 | End to End Functional testing - Schedule the extraction | Clear - Rohan | 1 | 2025-04-16 | 2025-04-17 | Not Started
EI-03-15 | UAT Obervsation if any | Eatgood | 4 | 2025-04-17 | 2025-04-23 | Not Started
EI-03-16 | Share the UAT Sign off email with Final UAT Observations | Clear - Shubham | 2 | 2025-04-23 | 2025-04-25 | Not Started
EI-03-17 | UAT Sign-off | EATGOOD Team | 1 | 2025-04-25 | 2025-04-28 | Not Started
EI-04 | Final Preparation & Go-Live |  | 6.75 | 2025-04-28 | 2025-05-06 | Not Started
| Configuring to allow API calls in ZOHO Prod | Clear - Shubham + EATGOOD Team | 1 | 2025-04-28 | 2025-04-29
EI-04-01 | Creating the Prod Environment for Config. Deployment | Clear - Shubham | 1 | 2025-04-29 | 2025-04-30 | Not Started
EI-04-02 | Update the sandbox config to prod | Clear - Rohan | 1 | 2025-04-30 | 2025-05-01 | Not Started
EI-04-04 | Sharing Prod auth token to Developer | Clear - Shubham | 0.25 | 2025-05-01 | 2025-05-01 | Not Started
EI-04-05 | Maintain connection parameters in Zoho (Prod to Clear Prod) | Clear - Rohan | 1 | 2025-05-01 | 2025-05-02 | Not Started
EI-04-06 | Final Code pack sharing to Prod environment | Clear - Rohan | 1 | 2025-05-02 | 2025-05-05 | Not Started
EI-04-09 | Schedule the extraction in production | Clear - Shubham | 0.5 | 2025-05-05 | 2025-05-05 | Not Started
EI-04-10 | GO LIVE for ID | EATGOOD Team | 1 | 2025-05-05 | 2025-05-06 | Not Started
EI-05 | Post Go-Live Production Support |  | 3 | 2025-05-06 | 2025-05-09 | Not Started
EI-05-01 | Post Go-Live Support | Clear - Shubham | 1 | 2025-05-06 | 2025-05-07 | Not Started
EI-05-02 | Issue Management & Support Review | Clear - Shubham | 1 | 2025-05-07 | 2025-05-08 | Not Started
EI-05-03 | Project Closing | Clear - Shubham | 1 | 2025-05-08 | 2025-05-09 | Not Started
EI-06 | Change requests post Go-Live |  |  |  |  | Not Started
Formulas:
Planned End Date = WORKDAY([Planned Start Date],[Tentative no. of days])
Planned Start Date = [Planned Start Date, row above]
Planned Start Date = [Planned End Date, row above]