## Pre Requisites
Sr. No | Pre-Req Type | Prerequisite Detail | Status | Remarks | Ownership
1 | Access Controls | VPN Connection for each Environment- SAP (to be set up on minimum two system) | Not Started
2 | Access Controls | SAP GUI Credentials for Dev Server | Not Started |  | IT Team
3 | Access Controls | SAP GUI Credentials for Quality Server | Not Started |  | IT Team
4 | Access Controls | ABAP ID & Functional ID (with Access right) | Not Started |  | IT Team
5 | Access Controls | PI/PO ID (with Access right) | Not Started |  | IT Team
6 | Access Controls | ZPACKAGE for storing the development program and Transport Request Guidelines for ERP (SAP S4 HANA). | Not Started |  | IT Team
7 | Access Controls | T-Codes Authorization on Quality Server Credentials for Quality System | Not Started |  | IT Team
8 | Access Controls | RFC Connection | Not Started |  | Basis Team
9 | Access Controls | Whitelisting of IP address to be done (On both networks i.e. XPEDIZE and Client) | Not Started |  | Basis team
10 | Development | Document Types used by Company in ERP for: 1. Open Invoices (including reversed invoices) 2. Adjustments 3. Clearing | Not Started |  | FI team
11 | Development | Company Codes (For which program needs to be developed) | Not Started |  | FI team
12 | Development | Special GL List for Advances | Not Started |  | FI team
13 | Development | One field in BKPF table (In SAP, this is to preserve old payment terms and baseline date). Usually we capture old payment term and baseline date in BKPF-XREF1_HD | Not Started |  | FI team
14 | Development | GL account for posting Dr/Cr notes (Cash discount GL number and SCF Program GL number) *SCF: Supply Chain Financing | Not Started |  | FI team
15 | Development | Accounting groups that need to excluded from Vendor Master | Not Started |  | FI team
17 | Testing | Test data (On development of program, test cases covering all the possible scenarios to be provided by client) | Not Started |  | FI team
18 | Details required on Production Server | Production User ID (In production server to set up schedule background jobs) post successful testing in Quality server. | Not Started |  | FI team

## Tcodes
Tcode | Description
SM59 | RFC
SE09 | TR movement
STRUST | RFC
SE16N | Tables
SE16 | Tables
SE11 | Table structure
SE37 | Function Module details
SE38 | Program details
SE80 | FM execution
F-43 | Invoice Creation
F-53 | Vendor Payments
FB01 | Document posting
FB08 | Document reversal
FB03 | Document display
SU53 | Authorization status
FBL1N | Vendor Line Item display
FBL3N | GL Line item displa
FS00 | G/L Account display
FS02 | G/L Account change
FS01 | G/L Account create

## Posting Options
|  | Amount | Due date
Invoice | KR/RE | -100 | 23-08-2024
Discount | KG | 2 | 27-07-2024
Maturity | AB | -98 | 27-07-2024
Posting Model 1 |  | Posting only KG, Updating original Invoice due date to immediate, No clearing
Posting Model 2 |  | Posting KG No update to Original Invoice Clearing of Invoice and KG document to create new payable due immediately